## Product Backlog
Group | SWAPP Team
Section | 11
Members | Names |  | Number of User Stories Assigned (automatic calculated, no need to fill in)
1 | Abdulkader Sardini |  | 4
2 | Sohaib Belaroussi |  | 3
3 | Musab Mudathir |  | 4
4 | Ibtesham Ahmed Promit |  | 3
PRODUCT BACKLOG
User Story ID | As a/an(Buyer/ Seller) | I want (functionality or feature) | So that (benefit) | Assignee | Release on
US001 | Buyer | to be able to create a profile | I can view and buy products. | Sohaib Belaroussi | Sprint 1
US002 | Buyer | to be able to login to the app | I can view the recently posted product ads. | Ibtesham Ahmed Promit | Sprint 1
US003 | Buyer | to view all the listed items on the app | I can choose which product to buy. | Abdulkader Sardini | Sprint 1
US004 | Buyer | to have a search box | to find items. | Musab Mudathir | Sprint 1
US005 | Buyer | to sort items by category | my search becomes easier. | Abdulkader Sardini | Sprint 3
US006 | Buyer | to be able to contact the seller | I can inquire about the product. | Abdulkader Sardini | Sprint 2
US007 | Buyer | to be able to leave comments under ad posts | I can make suggestions and requests. | Musab Mudathir | Sprint 2
US008 | Seller | buyers to leave ratings | I can improve my performance and have a more appealing profile. | Ibtesham Ahmed Promit | Sprint 3
US009 | Seller | to be able to create a profile | I can sell my items. | Sohaib Belaroussi | Sprint 1
US010 | Seller | be able to login to the app using email and password | I can post and modify my ads. | Ibtesham Ahmed Promit | Sprint 1
US011 | Seller | to be able post my items in the app for sale, providing details like photos | descriptions, and price. | Sohaib Belaroussi | Sprint 1
US012 | Seller | my contact information to be displayed under my ad post | potential buyers can contact me. | Abdulkader Sardini | Sprint 2
US013 | Seller | to be able to view my currently listed ads | I have an overall view. | Musab Mudathir | Sprint 2
US014 | Seller | to see comments from potential buyers under my post | I can see their suggestions and inquiries. | Musab Mudathir | Sprint 2
US015 | Buyer | I want to have a wishlist | keep track of my favorite ads. | Abdulkader Sardini | Sprint 3